## Start Here
Labor Request Form
| Enter Show Information: |  |  |  | Check-In Information:
| Start Date: | 2022-09-28 | Names of technicians is not required. If the position is being filled by a Full-Time Employee, please reflect that below under the name tab. Enter IATSE 122 if the position is being filled by Union. INCLUDE IN AND OUT TIMES FOR THE DAYS. |  | Labor Request Tab:
| End Date: | 2022-09-29
| Employer: | John Doe LLC
| Show: | ICSC 2022 Western Conference
| Show Location: | San Diego Convention Center - Hall B2
| PM/Coordinator: | John Doe
Show Notes: Location: Hall B2 I Setup: Sept. 28th 8AM. Setup will be (4) 9X16 screens rear projection, (1) 10X30 screen for backdrop rear projection, Nexo line array system, pipe and drape, 40' lighting truss flown with Mac Auras. Show Room Floor Theatre is a small general session with 2-70" monitors on stands. In addition there will be two breakouts on the Mezzanine levels with cradle screens and sound (these go just one time at 9AM on the 29th. We will have one semi trailer to unload. Show time for Hall B2 is 11AM on the 29th, strike beginning at 3PM on the 29th as well. Strike for the Show Floor Theatre will be on the 30th at 10AM.

## Labor Request
|  |  |  | ICSC 2022 Western Conference SDCC General Session | [5 empty] | Check-In: | [6 empty] | ICSC 2022 Western Conference SDCC General Session |  |  |  |  | Check-In:
Position: | Name/Company: | # | Notes: |  | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-04 | 2022-10-05 | # | # | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | #
Video Engineer | IATSE 122 | 1 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 1 | 1 | [9 empty] | 1
Projectionist | IATSE 122 | 2 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 2 | 2 | [9 empty] | 2
Graphics | IATSE 122 | 3 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 3 | 3 | [9 empty] | 3
Camera Operator | IATSE 122 | 4 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 4 | 4 | [9 empty] | 4
Audio Engineer | IATSE 122 | 5 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 5 | 5 | [9 empty] | 5
L1 | IATSE 122 | 6 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 6 | 6 | [9 empty] | 6
Shader | IATSE 122 | 7 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 7 | 7 | [9 empty] | 7
Project Manager | IATSE 122 | 8 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 8 | 8 | [9 empty] | 8
Lighting Director | IATSE 122 | 9 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 9 | 9 | [9 empty] | 9
Spyder Operator | IATSE 122 | 10 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 10 | 10 | [9 empty] | 10
Camera Switch | IATSE 122 | 11 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 11 | 11 | [9 empty] | 11
Graphics | IATSE 122 | 12 | Setup 28th, show/strike 29th |  | 8AM-5PM | 10AM-7PM | [6 empty] | 12 | 12 | [9 empty] | 12
Loader | IATSE 122 | 13 | Setup 28th, show/strike 29th |  | 8AM-1PM | 5PM-9PM | [6 empty] | 13 | 13 | [9 empty] | 13
Loader | IATSE 122 | 14 | Setup 28th, show/strike 29th |  | 8AM-1PM | 5PM-9PM | [6 empty] | 14 | 14 | [9 empty] | 14
Loader | IATSE 122 | 15 | Setup 28th, show/strike 29th |  | 8AM-1PM | 5PM-9PM | [6 empty] | 15 | 15 | [9 empty] | 15
Loader | IATSE 122 | 16 | Setup 28th, show/strike 29th |  | 8AM-1PM | 5PM-9PM | [6 empty] | 16 | 16 | [9 empty] | 16
Steward | IATSE 122 | 17 | Setup 28th, show/strike 29th |  | 8AM-1PM | 8AM-9PM | [6 empty] | 17 | 17 | [9 empty] | 17
|  | 18 | [10 empty] | 18 | 18 | [9 empty] | 18
|  | 19 | [10 empty] | 19 | 19 | [9 empty] | 19
|  | 20 | [10 empty] | 20 | 20 | [9 empty] | 20
|  | 21 | [10 empty] | 21 | 21 | [9 empty] | 21
|  | 22 | [10 empty] | 22 | 22 | [9 empty] | 22
|  | 23 | [10 empty] | 23 | 23 | [9 empty] | 23
|  | 24 | [10 empty] | 24 | 24 | [9 empty] | 24
|  | 25 | [10 empty] | 25 | 25 | [9 empty] | 25
|  | 26 | [10 empty] | 26 | 26 | [9 empty] | 26
|  | 27 | [10 empty] | 27 | 27 | [9 empty] | 27
|  | 28 | [10 empty] | 28 | 28 | [9 empty] | 28
|  | 29 | [10 empty] | 29 | 29 | [9 empty] | 29
|  | 30 | [10 empty] | 30 | 30 | [9 empty] | 30
|  | 31 | [10 empty] | 31 | 31 | [9 empty] | 31
|  | 32 | [10 empty] | 32 | 32 | [9 empty] | 32
|  | 33 | [10 empty] | 33 | 33 | [9 empty] | 33
|  | 34 | [10 empty] | 34 | 34 | [9 empty] | 34
|  | 35 | [10 empty] | 35 | 35 | [9 empty] | 35
|  | 36 | [10 empty] | 36 | 36 | [9 empty] | 36
|  | 37 | [10 empty] | 37 | 37 | [9 empty] | 37
|  | 38 | [10 empty] | 38 | 38 | [9 empty] | 38
|  | 39 | [10 empty] | 39 | 39 | [9 empty] | 39
|  | 40 | [10 empty] | 40 | 40 | [9 empty] | 40
|  | 41 | [10 empty] | 41 | 41 | [9 empty] | 41
|  | 42 | [10 empty] | 42 | 42 | [9 empty] | 42
|  | 43 | [10 empty] | 43 | 43 | [9 empty] | 43
|  | 44 | [10 empty] | 44 | 44 | [9 empty] | 44
|  | 45 | [10 empty] | 45 | 45 | [9 empty] | 45
|  | 46 | [10 empty] | 46 | 46 | [9 empty] | 46
|  | 47 | [10 empty] | 47 | 47 | [9 empty] | 47
|  | 48 | [10 empty] | 48 | 48 | [9 empty] | 48
|  | 49 | [10 empty] | 49 | 49 | [9 empty] | 49
|  | 50 | [10 empty] | 50 | 50 | [9 empty] | 50
|  | 51 | [10 empty] | 51 | 51 | [9 empty] | 51
|  | 52 | [10 empty] | 52 | 52 | [9 empty] | 52
|  | 53 | [10 empty] | 53 | 53 | [9 empty] | 53
|  | 54 | [10 empty] | 54 | 54 | [9 empty] | 54
|  | 55 | [10 empty] | 55 | 55 | [9 empty] | 55
|  | 56 | [10 empty] | 56 | 56 | [9 empty] | 56
|  | 57 | [10 empty] | 57 | 57 | [9 empty] | 57
|  | 58 | [10 empty] | 58 | 58 | [9 empty] | 58
|  | 59 | [10 empty] | 59 | 59 | [9 empty] | 59
|  | 60 | [10 empty] | 60 | 60 | [9 empty] | 60
|  | 61 | [10 empty] | 61 | 61 | [9 empty] | 61
|  | 62 | [10 empty] | 62 | 62 | [9 empty] | 62
|  | 63 | [10 empty] | 63 | 63 | [9 empty] | 63
|  | 64 | [10 empty] | 64 | 64 | [9 empty] | 64
|  | 65 | [10 empty] | 65 | 65 | [9 empty] | 65
|  | 66 | [10 empty] | 66 | 66 | [9 empty] | 66
|  | 67 | [10 empty] | 67 | 67 | [9 empty] | 67
|  | 68 | [10 empty] | 68 | 68 | [9 empty] | 68
|  | 69 | [10 empty] | 69 | 69 | [9 empty] | 69
|  | 70 | [10 empty] | 70 | 70 | [9 empty] | 70
|  | 71 | [10 empty] | 71 | 71 | [9 empty] | 71
|  | 72 | [10 empty] | 72 | 72 | [9 empty] | 72
|  | 73 | [10 empty] | 73 | 73 | [9 empty] | 73
|  | 74 | [10 empty] | 74 | 74 | [9 empty] | 74
|  | 75 | [10 empty] | 75 | 75 | [9 empty] | 75
|  | 76 | [10 empty] | 76 | 76 | [9 empty] | 76
|  | 77 | [10 empty] | 77 | 77 | [9 empty] | 77
|  | 78 | [10 empty] | 78 | 78 | [9 empty] | 78
|  | 79 | [10 empty] | 79 | 79 | [9 empty] | 79
|  | 80 | [10 empty] | 80 | 80 | [9 empty] | 80
|  | 81 | [10 empty] | 81 | 81 | [9 empty] | 81
|  | 82 | [10 empty] | 82 | 82 | [9 empty] | 82
|  | 83 | [10 empty] | 83 | 83 | [9 empty] | 83
|  | 84 | [10 empty] | 84 | 84 | [9 empty] | 84
|  | 85 | [10 empty] | 85 | 85 | [9 empty] | 85
|  | 86 | [10 empty] | 86 | 86 | [9 empty] | 86
|  | 87 | [10 empty] | 87 | 87 | [9 empty] | 87
|  | 88 | [10 empty] | 88 | 88 | [9 empty] | 88
|  | 89 | [10 empty] | 89 | 89 | [9 empty] | 89
|  | 90 | [10 empty] | 90 | 90 | [9 empty] | 90
|  | 91 | [10 empty] | 91 | 91 | [9 empty] | 91
|  | 92 | [10 empty] | 92 | 92 | [9 empty] | 92
|  | 93 | [10 empty] | 93 | 93 | [9 empty] | 93
|  | 94 | [10 empty] | 94 | 94 | [9 empty] | 94

## Lists (hidden)
Stagehand | Travelling
Loader | IATSE 122
Strike Crew
Strike Tech
Lead AV Tech
Exhibits Lead
AV Tech
Multi-Source
Floater
Fork Op
Etcp Rigger
Lead Rigger
Rigger
V2
V1
Vid Eng.
Vid. Crew
Projectionist
Playback
GFX
Shader
Robo Cam.
Handheld Cam
LongLense Cam
Camera
LED Lead
A2
A1
Aud Eng.
Aud Crew
L2
L1
LD
M.E
Elec Crew
Spotlight
Records
Spkr Rdy
IT
Zoom
Vmix
Hybrid Tech
Stream Tech
PM
TD
Producer
Steward
Head Carpenter
Carp
Web Op
IT Lead